## backlog
Priority 1
1	simplest case, is definitively needed
2	different case, is definively needed
3	Less likely case, need is dependent on outcome of ½
4	different version/extension of the program, not essential
5	extra
ID	I want	so that	Notes	Priority	Status
0.1	to find siRNA-Complement-kmers in downregulated mRNA	I can check, that inhibition works	can also be used as quality control for the program	1	not started
0.2	to find siRNA-off target effects	I can check experiment-/drug design	main story of the program	2	not started
0.3	to find miRNA-Complement-kmers in down-/upregulated mRNA	I can check, if my KO/KI worked	can also be used as quality control for the program	2	started
1.0	to read a formatted expression level list	the program runs on my data		1	finished
1.1	not to care about the format of the list	preprocessing is made easier	maybe technical minimal requirements? Filename parsed?	2	not started
1.2	not to care about the titles of the table	preprocessing is made easier	probably contradicts 1.2	3	finished
1.3	that seqan can work on my expression level list	the program is efficent		1	finished
1.4	to parse an absolute cutoff for the expression list	I can concentrate on downregulated genes		1	finished
1.5	to parse an relative cutoff, e.g. the top 10%	I can check genes, whose expression levels are similar		2	not started
1.6	that the statistics for cutoff is calculated internally	usage becomes simpler		4	not started
1.7	to work on multiple expression lists with the same set of kmers	I can check my iRNA in different systems, e.g. different tissue	goes along with 2.5	5	not started
2.1	to generate a list of all possible 6mers	kmer search is not biased		1	not started
2.2	to generate a list of all possible 7mers	kmer search is not biased		2	not started
2.3	to generate a list of all possible 8mers	kmer search is not biased		2	not started
2.4	to parse a list of preselected kmers	the program is specific and efficient	goes along with 2.5 and 1.7	3	not started
2.5	that kmers can be stored efficiently	I don't have to waste time on generating them de novo, evtl. print them to a file	goes along with 1.7, implementation can be combined with 2.4 via command line argument/default argument	3	not started
2.6	kmer generation to be efficient	I will save time		2	not started
2.7	to be able to parse the kmer size	I can be more flexible		3	not started
2.8	to be able to specifiy the kmers more (e.g. GC content)	I will be able to design iRNAs	is of use in iRNA design, because of different stability, substructures, etc.	5	not started
3.1	to find kmers in the reduced expression level list	I can identify potential (off)target effects		1	not started
3.2	to compare different kmer-search implementations	I can choose the best		4	not started
3.3	the found kmers to be stored in a contingengy table	I can perform statistics		1	not started
3.4	the contingency table to be printed	I can manually double check		3	not started
3.3	to allow for non-exact search	I can include possible mutations	only for given kmer-Lists, not if all kmers are checked, kind of allowed mismatches should be specified, e.g. CpG-island targets, only relevant for few applications	5	not started
4.1	to perform the Fisher's test on the contingency table	I know which kmer are significant in downregulated genes		1	not started
4.2	to have multiple testing correction	I can check many kmers at once	depends on the outcome: how many kmers are found at all? Which testing correction should be used?	2	not started
4.3	to check the influence of different statistical tests on the number of top-hits kmers	I can exlude artifically low/ high numbers of top-hits		4	not started
4.4	to parse the kind of statistical test via command line	I can choose the test based on my application	depends on outcome of 4.1 and 3.4, all possible test have to be implemented internally	5	not started
4.5	the contingency table to shrink to kmers, that reach a certain level of significance	I can gain insight at first glance		1	not started
4.6	to parse the level of significance for statistical test	I remain in control over the broadness of my request		2	not started
4.7	to print out the reduced contingency table in a nicely formatted way	I can think about biological implications	if this step is completed, 3.4 becomes obsolet	1	not started
4.8	to print out a list with all the results in a nicely formatted way	I can process and share the outcome	should include sequences, expression levels, p-values	1	not started
5.1	to have a KNIME node for reading the expression level list and saving the top/downregulated mRNAs	I can give the list of relevant mRNAs to other programs	how can the cutoff be incooperated?	3	not started
5.2	to have a KNIME node to generate kmers	I can give the list of kmers to other programs	only if 2.5 is accomplished	3	not started
5.3	to have a KNIME node to combine kmer-list and mRNA list into contingency table	I can perform statistics and show the table to coworkers		3	not started
5.4	to have a KNIME node to perform statistical testing on the contingency table	I can have a whole KNIME workflow	Does this exist already? Check with 4.X in terms of which test, etc.	3	not started
5.5	to have a KNIME node that visualizes the outcome	I can display my results more obviously	see SYLAMER paper	4	not started
5.6	to have an R-Script for visualization of the outcome	I can display my results more obviously	only if 5.5 is not satisfying	5	not started
5.7	incooperate my R-Script into the KNIME workflow	I can display my results more obviously	only if 5.5 is not satisfying, goes together with 5.6	5	not started
6.0	to the program to be faster than SYLAMER in total	I don't have to use SYLAMER		1	not started

## burnDown
UserStory Ids	Name	Type	Estimated Date	Actual Date	total #jobs	Date	Ideal #remaining jobs	Actual #remaining jobs
1.4, 1.0, 1.1, 1.3	process expression level list	Coding	04/20/16	05/08/16	30	04/18/16	30	30
2.1, 2.6	generate all possible 6mers	Coding	04/21/16			04/20/16	29	30
3.1, 3.3, 3.4	contingency table for 6mers	Coding	04/22/16			04/22/16	27	30
4.1, 4.2	fishers test on contingency table	Coding	04/25/16			04/24/16	27	30
4.5, 4.6, 4.7	save significant kmers	Coding	04/26/16			04/26/16	25	30
4.8	generate output list	Coding	04/27/16			04/28/16	24	30
	ReadtheDocs for Sprint1/2	Documentation	04/28/16			04/30/16	22	30
6.0, 0.1, 0.2, 0.3	measure speed and accurancy for different test cases	Testing	04/29/16			05/02/16	21	30
4.2	include multiple testing corrction	Coding	04/29/16			05/04/16	18	30
1.1/1.2, 1.5	improve reading of expression list	Coding	05/02/16			05/06/16	17	30
2.2, 2.3, 2.7	extension for generation of 7mers and 8mers	Coding	05/03/16			05/08/16	17	29
6.0	measure speed and accuracy	Testing	05/03/16			05/10/16	15	27
2.4, 2.5, 2.6, 6.0	enhance efficiency of kmer-generation	Planing/Reading/Ideas	05/04/16			05/12/16	13	25
2.4, 2.5, 2.6, 6.0	enhance efficiency of kmer-generation	Coding, Testing	05/06/16			05/14/16	11	23
	ReadtheDocs for Sprint3	Documentation	05/09/16			05/16/16	10	22
3.2, 6.0	Change Search Algorithm to indexed Search	Coding	05/10/16			05/18/16	8	19
3.2, 6.0	try different search algorithms, test speed	Coding, Testing	05/11/16			05/20/16	6	17
3.2, 6.0	Change Search Algorithm to JST	Coding	05/12/16			05/22/16	6	17
3.2, 6.0	try different search algorithms, test speed	Coding, Testing	05/13/16			05/24/16	3	13
	documentation of speed enhancement	Documentation	05/14/16			05/26/16	1	13
	readtheDocs for Sprint4	Documentation	05/16/16			05/28/16	0	13
1.6	improve statistics by change of cutoff for expression list	coding	05/17/16			05/30/16		13
4.3	improve statistics by exchange of Fisher's test	coding	05/18/16
	report for program so far, including test results	Coding	05/19/16
	report for program so far, including test results	Coding	05/20/16
5.1, 5.2	KNIME nodes from expression list to kmer generation	Coding	05/23/16
5.3, 5.4	KNIME nodes from contingency list to statistics	Coding	05/24/16
5.5, 5.6, 5.7	visualization with KNIME/R	Coding	05/25/16
	Document program (presentation)	Documentation	05/26/16
	Document program (presentation)		05/27/16

## Sprintlog1
User-story ID	Tasks	Method/variable name	Day1	Day2	Day3	Day4	Day5	estimated hours	actual hours	overspend
1.4	setup SeqAn working environment							2	2	0
1.0	parse cutoff	cutoff						1.6	1	-0.6
1.1	research how to read files in C++							4	4	0
1.3	code file reading: until line#=cutAbs	getExpLev						0	4	4
1.3	read mRNA sequence, add to StringSet	matchMRNA						4	9	5
1.3	use testingFunction from SeqAn							2
2.1/2.6	write Travis TestCase							postponed
2.1/2.6	brainstorm how to generate kmers efficiently							6.4
2.1/2.6	permutation?							0
2.1/2.6	tree?							0
2.1/2.6	implement method to generate 1 subset	makeKmer/makeKmers						1.6
2.5	store kmers into StringSet	kmerToSet						4
2.1/2.6	implement printing of kmers to a txt file							0.8
2.1/2.6	Travis for makeKmer							postponed
3.1	Travis for kmerToSet							postponed
3.3	find kmers in mRNA sequences with Aho-Corasick	AhoSearchSet						0.8
3.3	read how to make tables in C++							1.6
3.3	write contingency table							2.4
	print contingency table							1.6
	Write SprintLog2, update issue list							2.4	1	-1.4
	revise C++: headers and include							2	2.5	0.5
							total	37.2	23.5	7.5

## Sprintlog2
User-story ID	Tasks	Method/variable name	Day1	Day2	Day3	Day4	Day5	estimated hours	actual hours	overspend
1.3	seperate filereading into headers, change CMAKE	GetExpLev, matchMRNA	0.5					2	0.5	-1.5
2.1/2.6	brainstorm how to generate kmers efficiently			2				6.4	2	-4.4
2.1/2.6	permutation?							0	0	0
2.1/2.6	tree?							0	0	0
2.1/2.6	implement method to generate 1 subset	makeKmer/makeKmers		2				1.5	2	0.5
2.5	store kmers into StringSet	kmerToSet		1.5				4	1.5	-2.5
2.1/2.6	implement printing of kmers to a txt file							0.8	0	-0.8
3.3	find kmers in mRNA sequences with Aho-Corasick	countFinds.cpp			8			0.8	8	7.2
3.3	read how to make tables in C++							2	0	-2
3.3	write contingency table			2		7		2.5	9	6.5
3.3	print contingency table							2	0	-2
4.1	Implement Fishers Test in C++	fishers.cpp REQUIRES BOOST LIBRARY					7	4	7	3
4.5	the contingency table to shrink to kmers, that reach a certain level of significance						1	2	1	-1
4.7	to print out the reduced contingency table in a nicely formatted way							2	0	-2
4.8	to print out a list with all the results in a nicely formatted way							4	0	-4
1.3	write method that can read preprocessed expression data	GetTransc in inputTransc.cpp	4					2	4	2
1.3	Options: either preprocessed input or combined from mRNA list+ expression data							1	0	-1
	learn Travis							1	0	-1
	write test cases sprint2							1	0	-1
	automatic testing with Travis							2	0	-2
	readthedocs for Sprint1 and 2							3	0	-3
									0	0
									0	0
			4.5	7.5	8	7	8	44	35	-9

## SprintLog3
User-story ID	Tasks	Method/variable name	Day2	Day3	Day4	Day5	estimated hours	actual hours	overspend
	Multiple Testing Correction		0.5	6			3	6.5	3.5
	Contingency Table of Lists instead List of Contingencies		3				6	3	-3
	Indexing over kmers (qgram)			3.5		6	6	9.5	3.5
	print out kmers						2	0	-2
	print out results			0.5			2	0.5	-1.5
	read kmers from external list						2	0	-2
	testing correctness				2	3	4	5	1
	testing velocity						8	0	-8
	improve velocity		4				6	4	-2
	documentation (report)						8	0	-8
	significance level as command line argument				0		0.5	0	-0.5
	fix bugs		2	1	1		4	4	0
	relative cutoff				1		4	1	-3
	multiple cutoffs					3	2	3	1
	sort out options and arguments				2.5		2	2.5	0.5
	Planning/Discussion				1		1	1	0
	adapt matchMRNA.cpp and expLev.cpp for use with the new command line parsing						3	0	-3

	TOTAL		9.5	11	7.5	12	63.5	40	-23.5

## SprintLog4
Tasks	Method/variable name	Day1	Day2	Day3	Day4	Day5	estimated hours	actual hours	overspend
write report		6	5				8	11	3
set up sylamer		2					1	2	1
Test velocity (4 Test Cases)		4			5		6	9	3
Documentation: ReadTheDocs							8	0	-8
Correctness: Seqan Test Script					5		4	5	1
Make Presentation						10	10	10	0
Update Planning				2			2	2	0
								0	0
								0	0
								0	0
								0	0
								0	0
								0	0
								0	0
								0	0
								0	0
								0	0

TOTAL		12	5	2	10	10	39	39	0