## backlog
Priority 1
1	simplest case, is definitively needed
2	different case, is definively needed
3	Less likely case, need is dependent on outcome of ½
4	different version/extension of the program, not essential
5	extra
ID	I want	so that	Notes	Priority	Status
0.1	to find siRNA-Complement-kmers in downregulated mRNA	I can check, that inhibition works	can also be used as quality control for the program	1	not started
0.2	to find siRNA-off target effects	I can check experiment-/drug design	main story of the program	2	not started
0.3	to find miRNA-Complement-kmers in down-/upregulated mRNA	I can check, if my KO/KI worked	can also be used as quality control for the program	2	started
1.0	to read a formatted expression level list	the program runs on my data		1	finished
1.1	not to care about the format of the list	preprocessing is made easier	maybe technical minimal requirements? Filename parsed?	2	not started
1.2	not to care about the titles of the table	preprocessing is made easier	probably contradicts 1.2	3	finished
1.3	that seqan can work on my expression level list	the program is efficent		1	finished
1.4	to parse an absolute cutoff for the expression list	I can concentrate on downregulated genes		1	finished
1.5	to parse an relative cutoff, e.g. the top 10%	I can check genes, whose expression levels are similar		2	not started
1.6	that the statistics for cutoff is calculated internally	usage becomes simpler		4	not started
1.7	to work on multiple expression lists with the same set of kmers	I can check my iRNA in different systems, e.g. different tissue	goes along with 2.5	5	not started
2.1	to generate a list of all possible 6mers	kmer search is not biased		1	not started
2.2	to generate a list of all possible 7mers	kmer search is not biased		2	not started
2.3	to generate a list of all possible 8mers	kmer search is not biased		2	not started
2.4	to parse a list of preselected kmers	the program is specific and efficient	goes along with 2.5 and 1.7	3	not started
2.5	that kmers can be stored efficiently	I don't have to waste time on generating them de novo, evtl. print them to a file	goes along with 1.7, implementation can be combined with 2.4 via command line argument/default argument	3	not started
2.6	kmer generation to be efficient	I will save time		2	not started
2.7	to be able to parse the kmer size	I can be more flexible		3	not started
2.8	to be able to specifiy the kmers more (e.g. GC content)	I will be able to design iRNAs	is of use in iRNA design, because of different stability, substructures, etc.	5	not started
3.1	to find kmers in the reduced expression level list	I can identify potential (off)target effects		1	not started
3.2	to compare different kmer-search implementations	I can choose the best		4	not started
3.3	the found kmers to be stored in a contingengy table	I can perform statistics		1	not started
3.4	the contingency table to be printed	I can manually double check		3	not started
3.3	to allow for non-exact search	I can include possible mutations	only for given kmer-Lists, not if all kmers are checked, kind of allowed mismatches should be specified, e.g. CpG-island targets, only relevant for few applications	5	not started
4.1	to perform the Fisher's test on the contingency table	I know which kmer are significant in downregulated genes		1	not started
4.2	to have multiple testing correction	I can check many kmers at once	depends on the outcome: how many kmers are found at all? Which testing correction should be used?	2	not started
4.3	to check the influence of different statistical tests on the number of top-hits kmers	I can exlude artifically low/ high numbers of top-hits		4	not started
4.4	to parse the kind of statistical test via command line	I can choose the test based on my application	depends on outcome of 4.1 and 3.4, all possible test have to be implemented internally	5	not started
4.5	the contingency table to shrink to kmers, that reach a certain level of significance	I can gain insight at first glance		1	not started
4.6	to parse the level of significance for statistical test	I remain in control over the broadness of my request		2	not started
4.7	to print out the reduced contingency table in a nicely formatted way	I can think about biological implications	if this step is completed, 3.4 becomes obsolet	1	not started
4.8	to print out a list with all the results in a nicely formatted way	I can process and share the outcome	should include sequences, expression levels, p-values	1	not started
5.1	to have a KNIME node for reading the expression level list and saving the top/downregulated mRNAs	I can give the list of relevant mRNAs to other programs	how can the cutoff be incooperated?	3	not started
5.2	to have a KNIME node to generate kmers	I can give the list of kmers to other programs	only if 2.5 is accomplished	3	not started
5.3	to have a KNIME node to combine kmer-list and mRNA list into contingency table	I can perform statistics and show the table to coworkers		3	not started
5.4	to have a KNIME node to perform statistical testing on the contingency table	I can have a whole KNIME workflow	Does this exist already? Check with 4.X in terms of which test, etc.	3	not started
5.5	to have a KNIME node that visualizes the outcome	I can display my results more obviously	see SYLAMER paper	4	not started
5.6	to have an R-Script for visualization of the outcome	I can display my results more obviously	only if 5.5 is not satisfying	5	not started
5.7	incooperate my R-Script into the KNIME workflow	I can display my results more obviously	only if 5.5 is not satisfying, goes together with 5.6	5	not started
6.0	to the program to be faster than SYLAMER in total	I don't have to use SYLAMER		1	not started

## burnDown
UserStory Ids	Name	Type	Estimated Date	Actual Date	total #jobs	Date	Ideal #remaining jobs	Actual #remaining jobs
1.4, 1.0, 1.1, 1.3	process expression level list	Coding	20.04.16	08.05.16	30	18.04.16	30	30
2.1, 2.6	generate all possible 6mers	Coding	21.04.16			20.04.16	29	30
3.1, 3.3, 3.4	contingency table for 6mers	Coding	22.04.16			22.04.16	27	30
4.1, 4.2	fishers test on contingency table	Coding	25.04.16			24.04.16	27	30
4.5, 4.6, 4.7	save significant kmers	Coding	26.04.16			26.04.16	25	30
4.8	generate output list	Coding	27.04.16			28.04.16	24	30
	ReadtheDocs for Sprint1/2	Documentation	28.04.16			30.04.16	22	30
6.0, 0.1, 0.2, 0.3	measure speed and accurancy for different test cases	Testing	29.04.16			02.05.16	21	30
4.2	include multiple testing corrction	Coding	29.04.16			04.05.16	18	30
1.1/1.2, 1.5	improve reading of expression list	Coding	02.05.16			06.05.16	17	30
2.2, 2.3, 2.7	extension for generation of 7mers and 8mers	Coding	03.05.16			08.05.16	17	29
6.0	measure speed and accuracy	Testing	03.05.16			10.05.16	15	27
2.4, 2.5, 2.6, 6.0	enhance efficiency of kmer-generation	Planing/Reading/Ideas	04.05.16			12.05.16	13	25
2.4, 2.5, 2.6, 6.0	enhance efficiency of kmer-generation	Coding, Testing	06.05.16			14.05.16	11	23
	ReadtheDocs for Sprint3	Documentation	09.05.16			16.05.16	10	22
3.2, 6.0	Change Search Algorithm to indexed Search	Coding	10.05.16			18.05.16	8	19
3.2, 6.0	try different search algorithms, test speed	Coding, Testing	11.05.16			20.05.16	6	18
3.2, 6.0	Change Search Algorithm to JST	Coding	12.05.16			22.05.16	6	18
3.2, 6.0	try different search algorithms, test speed	Coding, Testing	13.05.16			24.05.16	3	18
	documentation of speed enhancement	Documentation	14.05.16			26.05.16	1	18
	readtheDocs for Sprint4	Documentation	16.05.16			28.05.16	0	18
1.6	improve statistics by change of cutoff for expression list	coding	17.05.16			30.05.16		18
4.3	improve statistics by exchange of Fisher's test	coding	18.05.16
	report for program so far, including test results	Coding	19.05.16
	report for program so far, including test results	Coding	20.05.16
5.1, 5.2	KNIME nodes from expression list to kmer generation	Coding	23.05.16
5.3, 5.4	KNIME nodes from contingency list to statistics	Coding	24.05.16
5.5, 5.6, 5.7	visualization with KNIME/R	Coding	25.05.16
	Document program (presentation)	Documentation	26.05.16
	Document program (presentation)		27.05.16

## Sprintlog1
User-story ID	Tasks	Method/variable name	Day1	Day2	Day3	Day4	Day5	estimated hours	actual hours	overspend
1.4	setup SeqAn working environment							2	2	0
1.0	parse cutoff	cutoff						1,6	1	-0,6
1.1	research how to read files in C++							4	4	0
1.3	code file reading: until line#=cutAbs	getExpLev						0	4	4
1.3	read mRNA sequence, add to StringSet	matchMRNA						4	9	5
1.3	use testingFunction from SeqAn							2
2.1/2.6	write Travis TestCase							postponed
2.1/2.6	brainstorm how to generate kmers efficiently							6,4
2.1/2.6	permutation?							0
2.1/2.6	tree?							0
2.1/2.6	implement method to generate 1 subset	makeKmer/makeKmers						1,6
2.5	store kmers into StringSet	kmerToSet						4
2.1/2.6	implement printing of kmers to a txt file							0,8
2.1/2.6	Travis for makeKmer							postponed
3.1	Travis for kmerToSet							postponed
3.3	find kmers in mRNA sequences with Aho-Corasick	AhoSearchSet						0,8
3.3	read how to make tables in C++							1,6
3.3	write contingency table							2,4
	print contingency table							1,6
	Write SprintLog2, update issue list							2,4	1	-1,4
	revise C++: headers and include							2	2,5	0,5
							total	37,2	23,5	7,5

## Sprintlog2
User-story ID	Tasks	Method/variable name	Day1	Day2	Day3	Day4	Day5	estimated hours	actual hours	overspend
1.3	seperate filereading into headers, change CMAKE	GetExpLev, matchMRNA	0,5					2	0,5	-1,5
2.1/2.6	brainstorm how to generate kmers efficiently			2				6,4	2	-4,4
2.1/2.6	permutation?							0	0	0
2.1/2.6	tree?							0	0	0
2.1/2.6	implement method to generate 1 subset	makeKmer/makeKmers		2				1,5	2	0,5
2.5	store kmers into StringSet	kmerToSet		1,5				4	1,5	-2,5
2.1/2.6	implement printing of kmers to a txt file							0,8	0	-0,8
3.3	find kmers in mRNA sequences with Aho-Corasick	countFinds.cpp			8			0,8	8	7,2
3.3	read how to make tables in C++							2	0	-2
3.3	write contingency table			2		7		2,5	9	6,5
3.3	print contingency table							2	0	-2
4.1	Implement Fishers Test in C++	fishers.cpp REQUIRES BOOST LIBRARY					7	4	7	3
4.5	the contingency table to shrink to kmers, that reach a certain level of significance						1	2	1	-1
4.7	to print out the reduced contingency table in a nicely formatted way							2	0	-2
4.8	to print out a list with all the results in a nicely formatted way							4	0	-4
1.3	write method that can read preprocessed expression data	GetTransc in inputTransc.cpp	4					2	4	2
1.3	Options: either preprocessed input or combined from mRNA list+ expression data							1	0	-1
	learn Travis							1	0	-1
	write test cases sprint2							1	0	-1
	automatic testing with Travis							2	0	-2
	readthedocs for Sprint1 and 2							3	0	-3
									0	0
									0	0
			4,5	7,5	8	7	8	44	35	-9

## SprintLog3
User-story ID	Tasks	Method/variable name	Day2	Day3	Day4	Day5	estimated hours	actual hours	overspend
	Multiple Testing Correction		0,5	6			3	6,5	3,5
	Contingency Table of Lists instead List of Contingencies		3				6	3	-3
	Indexing over kmers (qgram)			3,5			6	3,5	-2,5
	print out kmers						2	0	-2
	print out results			0,5			2	0,5	-1,5
	read kmers from external list						2	0	-2
	testing correctness				2		4	2	-2
	testing velocity						8	0	-8
	improve velocity		4				6	4	-2
	documentation (report)						8	0	-8
	significance level as command line argument				0		0,5	0	-0,5
	fix bugs		2	1	0,5		4	3,5	-0,5
	relative cutoff				1		4	1	-3
	multiple cutoffs						2	0	-2
	sort out options and arguments				2,5		2	2,5	0,5
	Planning/Discussion				1		1	1	0
	adapt matchMRNA.cpp and expLev.cpp for use with the new command line parsing						3	0	-3

	TOTAL		9,5	11	7	0	63,5	27,5	-36